INVESTMENTS AND INNOVATIONS

Investments

The investment program of IDGC of Centre for 2010 was planned to disburse the capital investments in the amount of 11,82 billion roubles. Actually, for the accounting period 12,23 billion roubles were disbursed or 103 % from the plan.

For 2010 on modernisation and reconstruction of facilities of IDGC of Centre 6,64 billion roubles of capital investments against the plan of 6,2 billion roubles, or 107 % were disbursed. 5,59 billion roubles at the year plan of 5,62 billion roubles, or 99,4 % were disbursed on new construction and expansion in the accounting period. Fixed assets in the amount of 10 billion roubles, or 97 % from the plan, 4 155 km of electric power lines, or 142 % from the plan, transformer capacity of 1050 MVA, or 111 % from the plan were commissioned.

- Actual volumes of investments into 2006-2010

| Period | Disbursement, excluding VAT | Fixed Assets disbursement, excluding VAT |  | Financing, excluding VAT | Capacity installed |  | Power increase |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Billion rbl. | Billion rbl. | Billion rbl. |  | Km | MVA | Km | MVA |
| 2006 | 4,508 | 4,368 | 5,305 |  | 1 676 | 398 | 673 | 136 |
| 2007 | 7,839 | 6,371 | 9,250 |  | 3 428 | 698 | 1 945 | 418 |
| 2008 | 9,071 | 7,730 | 10,252 |  | 3 263 | 660 | 1 886 | 489 |
| 2009 | 6,529 | 7,687 | 6,440 |  | 2 414 | 877 | 1 449 | 685 |
| 2010 | 12,230 | 10,008 | 12,503 |  | 4 155 | 1050 | 2777 | 770 |

- Data about actual volume of investments for 2006-2010 with the breakdown by divisions is given in Appendix 5.

During 2010 within the activities of modernisation and reconstruction (retooling and modernization) 1537 km of  0,4-110 kV power lines were reconstructed and 480 MVA transformer capacity was commissioned, within the new construction, expansion and taking onto the books 2618 km of 0,4-110 kV electric power lines and 570 MVA was commissioned. At the end of 2010 the length of electric power lines of the Company amounted to 374 thousand km. Capacity of 35-110kV substations reached 31404 MVA, of 6-10/0,4kV - 15192 MVA.

The planned values following the results of work for 2010 were executed for all indicators. The plan overfulfillment on disbursement of capital investments within the Investment program is due to performance of works on technological connection of consumers which were not planned in survey and design activities for 2010.

- Area and structure of capital investments, million rbl.

| IDGC of Centre, JSC | 2006 | 2007 | 2008 | 2009 | 2010 |
| --- | --- | --- | --- | --- | --- |
| Structure of investment activity – in total | 4504 | 7839 | 9071 | 6 529 | 12 230 |
| Electric grid facilities, including | 3 579 | 6 125 | 7 596 | 5473 | 9 045 |
| Automation, communication | 210 | 525 | 699 | 406 | 400 |
| Metering and electric power control devices, including | 230 | 208 | 163 | 242 | 497 |
| AMI for the wholesale market as a part of the investment program | 187 | 181 | 84 | 64 | 93 |
| AMI for the retail market and other means of the account and electric power control | 43 | 27 | 79 | 178 | 404 |
| EAD in progress for the next years | 28 | 210 | 203 | 94 | 195 |
| Other industrial and commercial facilities | 275 | 439 | 497 | 117 | 212 |
| Equipment, not included into cost calculation of new construction | 178 | 279 | 292 | 224 | 623 |
| Non production facilities | 1 | 0 | 1 | 0 | 0 |
| Capital investments in intangible assets | 27 | 13 | 0 | 0 | 0 |
| Long-term financial investments |  |  |  |  | 1 100 |
| Acquisition of fixed assets | 187 | 565 | 320 | 379 | 559 |
| Areas of investment activity – in total | 4504 | 7839 | 9071 | 6 529 | 12 230 |
| Technical reequipment and reconstruction | 2133 | 4081 | 5596 | 3 392 | 6 637 |
| including electric grid facilities | 1 695 | 3 497 | 4 761 | 2957 | 5 596 |
| New construction and expansion of existing facilities | 2184 | 3193 | 3155 | 2758 | 5 593 |
| including electric grid facilities | 1 884 | 2 628 | 2 835 | 2516 | 3 449 |
| Acquisition of fixed assets | 187 | 565 | 320 | 379 | 559 |
| For reference only: |  |  |  |  |  |
| Capital investments disbursement for new connections of customers | 677 | 2 446 | 3 486 | 2 188 | 3 832 |

The main causes of deviations from the planned targets on financing, disbursement of capital investments and capacity commissioning are:

- deviations on financing volume are caused by payment terms under contracts with contractors and suppliers of the equipment

- taking ownerless networks onto the books

Use of sources on investment activity

million rbl.

|  |  | 2010 |
| --- | --- | --- |
|  | Sources of investments, total | 12 230 |
| Own sources of financing | Depreciation of the reporting year | 3 428 |
|  | Unused depreciation of previous years | 0 |
|  | Unused profit of previous years | 58 |
|  | Profit of the reporting year for use in the investment program of the reporting year | 3 364 |
|  | Renovation included in the tariff | 2 499 |
|  | The sale of core non-current assets | 0 |
|  | The sale of non-core non-current assets | 0 |
|  | New connection fee | 865 |
|  | Other own sources of financing | 0 |
| External sources of financing | Budgetary funds (federal, municipal) | 0 |
|  | Borrowed funds (loan interest) | 4 329 |
|  | Borrowed funds (additional issue) | 0 |
|  | New connection fee | 1052 |
|  | Other sources of external funding, including share in construction using other sources |  |

The coming years the dynamics of capital investments has a positive tendency. Approved by the Board of Directors of the Company the volume of the investment program for 2011 is increased in comparison with the volume of 2010 by 39 %.

The investment program in 2011 — 2016 with the breakdown by divisions

|  |  |  |  |  |  | million rbl. |
| --- | --- | --- | --- | --- | --- | --- |
| Name of division | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 |
| Belgorodenergo | 4 053 | 4 864 | 5 513 | 5 853 | 5 901 | 5 901 |
| Bryanskenergo | 763 | 1 344 | 1 816 | 2 839 | 2 710 | 2 710 |
| Voronezhenergo | 2 180 | 1 728 | 4 932 | 2 880 | 5 330 | 5 330 |
| Kostromaenergo | 877 | 1 407 | 2 440 | 2 786 | 2 747 | 2 747 |
| Kurskenergo | 1 198 | 996 | 2 291 | 2 524 | 2 781 | 2 870 |
| Lipetskenergo | 3 190 | 2 673 | 2 959 | 3 279 | 3 635 | 3 635 |
| Orelenergo | 500 | 449 | 1 419 | 3 583 | 2 062 | 2 263 |
| Smolenskenergo | 1 600 | 2 400 | 3 350 | 4 414 | 4 850 | 4 850 |
| Tambovenergo | 902 | 1 124 | 818 | 1 431 | 1 454 | 1 100 |
| Tverenergo | 1 177 | 4 313 | 4 079 | 3 789 | 4 097 | 4 225 |
| Yarenergo | 1 225 | 1 308 | 1 160 | 1 175 | 1 202 | 1 257 |
| IDGC EXECUTIVE OFFICE | 12 | 15 | 17 | 18 | 19 | 19 |
| IDGC of Center | 17678 | 22 622 | 30 793 | 34 571 | 36 788 | 36 906 |
| Retooling and Modernization | 10 469 | 15 471 | 21 129 | 23 152 | 26 380 | 26 913 |
| New construction | 6 990 | 6 899 | 9 457 | 11 295 | 10 264 | 9 868 |
| Other | 219 | 252 | 208 | 124 | 144 | 126 |

The information on the areas of capital investments for 2011 — 2016 with the breakdown by divisions is given in Appendix 5.

- The ьфшт sources of financing of the investment program for 2011-2016 are:

- Depreciation

- New connection fee

- Use of bank credits for realisation of capital investments

- Profit of the fiscal year for use in the investment program

10 largest investment projects in 2010 with their key parametres

| Division | The project name | Investments (plan) in million rbl. | Investments (actual) in million rbl. | Actual/Planned in % | Commissioning of capacities (conditionalunit) |
| --- | --- | --- | --- | --- | --- |
| Belgorodenergo | Construction of 110/10kV SS "Krapivenskaya" with overhangs | 198, 507 | 201,382 | 101 % | 32 MVA |
| Belgorodenergo | AMI for the retail market | 313,7 | 270 | 86 % | 30376 pieces |
| Bryanskenergo | Reconstruction of 110/35/6kV SS "Pochep" to connect a plant on destruction of chemical weapons | 15,299 | 483,208 | 3158 % |  |
| Voronezhenergo | Reconstruction 35/6kV SS #10 with transfer to 110 kV voltage class | 101,868 | 108,007 | 106 % | 126 MVA |
| Kostromaenergo | Reconstruction of 35/6 kV SS "Vostochnaya-1" with transfer to 110 kV voltage class | 67,465 | 62,500 | 93 % |  |
| Lipetskenergo | Construction of 110kV SS "Manezhnaya" | 35,888 | 53,404 | 149 % | 40 MVA |
| Kurskenergo | Reconstruction and construction of OL-110 kV, indoor switchgear with 110kV SF6 insulated switchgear at SS-110/10kV "Boiler-house" to deliver power from KSZR TGK-4 | 447,085 | 385,877 | 86 % |  |
| Orelenergo | Reconstruction of 110kV SS "Zapadnaya" | 183,956 | 232,629 | 126 % | 63 MVA |
| Kurskenergo | Construction of 110/10 kV SS "Rodniki" | 133,304 | 133,123 | 100 % | 50 MVA |
| Yarenergo | Construction of 110/6/6 kV SS "Kotorosl" | 177,256 | 178,949 | 101 % | 50 MVA |