Appendix # 3.6

to the Annual Report of IDGC of Centre, PJSC

for 2015

Additional information on investment activity

Implementation of the investment program targets broken down by the branches

| Branch | Implementation of capital investment (mln RUB without VAT) |  |  | Financing (mln RUB with VAT) |  |  | km |  |  | MVA |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | plan | actual | % | plan | actual | % | plan | actual | % | plan | actual | % |
| Belgorodenergo | 3 399 | 3 485 | 103% | 4 010 | 4 089 | 102% | 1 205 | 1 218 | 101% | 231 | 245 | 106% |
| Bryanskenergo | 241 | 248 | 103% | 285 | 296 | 104% | 84 | 105 | 125% | 69 | 84 | 122% |
| Voronezhenergo | 1 158 | 1 264 | 109% | 1 298 | 1 442 | 111% | 278 | 480 | 173% | 265 | 323 | 122% |
| Kostromaenergo | 634 | 667 | 105% | 748 | 759 | 101% | 167 | 227 | 136% | 71 | 75 | 106% |
| Kurskenergo | 421 | 499 | 118% | 493 | 645 | 131% | 272 | 305 | 112% | 28 | 57 | 204% |
| Lipetskenergo | 1 008 | 1 056 | 105% | 1 190 | 1 371 | 115% | 165 | 275 | 167% | 71 | 71 | 99% |
| Orelenergo | 633 | 376 | 59% | 747 | 492 | 66% | 203 | 144 | 71% | 28 | 10 | 34% |
| Smolenskenergo | 1 012 | 1 113 | 110% | 1 194 | 1 327 | 111% | 357 | 402 | 113% | 38 | 39 | 104% |
| Tambovenergo | 1 306 | 1 268 | 97% | 1 413 | 1 404 | 99% | 262 | 288 | 110% | 58 | 68 | 117% |
| Tverenergo | 1 486 | 1 586 | 107% | 1 753 | 1 851 | 106% | 466 | 551 | 118% | 115 | 137 | 119% |
| Yarenergo | 1 399 | 1 410 | 101% | 1 551 | 1 508 | 97% | 682 | 790 | 116% | 94 | 119 | 127% |
| Total | 12 697 | 12 973 | 102% | 14 682 | 15 184 | 103% | 4 140 | 4 785 | 116% | 1 068 | 1 228 | 115% |

The deviation of the branch Tambovenergo to implement capital investments at 97% (- 3%) and financing at 99% (-1%) is due to saving following the results of procurement procedures without changing the physical volume of work performed (commissioning in kilometres – 110 %, commissioning in MVA – 117%).

As for the branch Orelenergo the deviation is caused by the following circumstances. Targets for 2015 were approved by the Orel Region Administration in the manner prescribed by the Governmental Resolution of the Russian Federation dated 01.12.2009 01.12.2009 №977, as part of the investment program of the branch Orelenergo in March 2014. Due to limited funding, in 2015 the Board of Directors of the Company approved the adjusted investment program of the branch Orelenergo for 2015, the figures of which were smaller than the previously approved values. The adjusted investment program of the branch in the established order was sent to the Orel Region Administration to be reviewed, but was not approved in 2015. In the absence of additional funding sources beyond the scope of the adjusted investment program of the branch, the approved investment program of the branch Orelenergo was performed not in full.

The most important projects in the investment program

| Name of a priority project of the investment program of a subsidiary | List of main activities | Scope of work performed in physical units | CAPEX mln RUB without VAT | Main engineering and economical performance |
| --- | --- | --- | --- | --- |
| Branch «Belgorodenergo» Reconstruction of SS 35 kV “Malinovka” to SS 110/35/10 with elimination of power shortage and replacement of 2 transformers 10 MVA for 16 MVA (Grid connection contract: №40301867 dated 08.04.11) | Area planning, road construction works, foundation construction, transformer installation, fencing construction, oil draining system construction | area planning of 8685 m2, road construction works- 1802 m2, foundation construction for transformer substation - 2 pc., transformer installation - 1 pc., foundation construction - 182 pc., fencing construction - 320 m, oil draining system construction | 32,34 | Reconstruction of Substation with transfer to 110 kV and installation of two transformers 16 MVA each. |
| Branch «Belgorodenergo» Reconstruction of SS 110/10 kV South. Replacement of power transformers 2х40 for 2х40 and 2х25 MVA, Switchgear-110, 10, 6kV, relay protection and automation panels; construction of a building for SF6 Switchgear-110kV, Switchgear-6 and 10 kV | EAD implementation phase “detailed design documentation” | The contract to perform design stage was concluded for the phase “detailed design documentation”. Stage “Project” was implemented in 2013 – a positive opinion was received. | 0 | Reconstruction of SS 110/10 kV with replacement of 2 power transformer at 40 MVA and installation of 2 additional transformers at 25 MVA. |
| Branch «Belgorodenergo» Reconstruction of SS-110kV Korocha with transfer of the substation to a new site. Instead of three transformers TDTN-16000/110/35/10 two transformers type TDTN-40000/110/35/10 to be installed | EAD implementation to reconstruct SS 110 kV with transfer to a new site. | In 2015 the design stage was completed. In 2016 it provides for implementation of the phase “detailed design documentation” and passage of the state review with the project approval | 0 | Reconstruction of SS 110 kV with transfer to a new site and installation of two transformers of 40 MVA each. |
| Branch «Voronezhenergo» Construction of 110 kV Cable of SS 220 kV Buturlinovka - SS 110 kV Buturlinovka-2 circuit 1,2 | EAD implementation to construct Cable 110 kV | 0 | 0,76 | double circuit Cable 110 kV performed with cable PvPu2g 3х(1х630/95) with its length of 0.54 km |
| Branch «Voronezhenergo» Modernization of SS 110 kV №9 SKHI with replacement of 110 kV switches | EAD implementation to replace 5 110 kV switches | 0 | 1 ,22 | Reconstruction of SS 110/10/6 kV №9 with replacement of 5 110 kV switches designed for 40 kA. (scheme of power distribution of Voronezh CHP-1) |
| Branch «Lipetskenergo» Construction of SS 110 kV Christmas (with transformers 2х25 MVA; Grid connection contract №40417928 dated 06.09.12 - LLC Motorinvest) | Construction of 2 cubicles of Outdoor Switchgear-110 kV, installation of a substation control building - switchgear and control gear-10 kV with 20 cubicles – 1 pc., installation of 2 auxiliary transformers, installation of 7 relay protection and automation panels, installation of two oil receivers and one oil drain tank, installation of one transformer of 25 MVA | Construction of 2 cubicles of Outdoor Switchgear-110 kV, installation of a substation control building - switchgear and control gear-10 kV with 20 cubicles – 1 pc., installation of 2 auxiliary transformers, installation of 7 relay protection and automation panels, installation of two oil receivers and one oil drain tank, installation of one transformer of 25 MVA | 44,61 | Construction of the first stage of SS 110 kV “Christmas” installation of one transformer of 25 MVA in 2015. |

Reasons for non-compliance or deviation from the planned figures by more than 5% of priority facilities

| # | Name of a priority project of the investment program of a subsidiary | Financing plan, mln RUB | Financing actual, mln RUB | % of implementation | CAPEX plan, mln RUB without VAT | CAPEX actual, mln RUB without VAT | % of implementation | Description of deviation reasons |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Branch «Belgorodenergo» Reconstruction of SS 35 kV Malinovka | 62,42 | 52,82 | 84 | 33,539 | 32,338 | 96 | Deviation in terms of financing arose from the difference between the planned and actual cost of purchased power transformers. |
| 2 | Branch «Voronezhenergo» Construction of 110 kV Cable of SS 220 kV Buturlinovka - SS 110 kV Buturlinovka-2 circuit 1,2 | 0,97 | 0,70 | 72 | 0,822 | 0,762 | 93 | Deviations in terms of implementation-reduction on the basis of tender procedures, in terms of financing- shift of timing of payment obligations |
| 3 | Branch «Voronezhenergo» Modernization of SS 110 kV №9 SKHI with replacement of 110 kV switches | 1,43 | 0.0 | 0.0 | 1,215 | 1,215 | 100.0 | Deviations in terms of financing- shifting payments to a subsequent period due to a change in the timing of the payment obligations |
| 4 | Branch «Lipetskenergo» Construction of SS 110 kV Christmas (with transformers 2х25 MVA; Grid connection contract №40417928 dated 06.09.12 - LLC Motorinvest) | 17,70 | 53,53 | 302 | 28,514 | 44,607 | 156 | Early completion of work |

Targets of the long-term Investment Program of IDGC of Centre for 2016-2020, duly approved in the regions of Russia and the Russian Ministry of Energy, and the draft of the adjusted long-term investment program for 2016-2021 (in terms of 2016-2020):

| Planned period |  |  | 2016 | 2017 | 2018 | 2019 | 2020 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CAPEX, mln RUB without VAT |  | Appr. plan | 13 387 | 13 941 | 14 697 | 15 187 | 16 057 |
|  |  | Adj. plan | 13 244 | 13 941 | 14 699 | 15 190 | 16 061 |
| Financing, mln RUB with VAT |  | Appr. plan | 16 194 | 16 418 | 17 375 | 17 911 | 18 968 |
|  |  | Adj. plan | 14 294 | 16 418 | 17 375 | 17 911 | 18 968 |
| Commissioning of fixed assets, mln RUB without VAT |  | Appr. plan | 13 694 | 14 199 | 14 932 | 15 593 | 16 043 |
|  |  | Adj. plan | 13 623 | 14 365 | 15 107 | 14 936 | 16 221 |
| Commissioned capacity | MVA | Appr. plan | 803 | 739 | 854 | 1049,2 | 572,6 |
|  |  | Adj. plan | 833,7 | 850,6 | 923,4 | 763,4 | 608,3 |
|  | km | Appr. plan | 4 200 | 4 394 | 4 773 | 4 438 | 5 819 |
|  |  | Adj. plan | 3 550 | 4 222 | 4 425 | 4 308 | 5 160 |

25 February 2016 a meeting of the Board of Directors of IDGC of Centre was held, which approved the adjusted Investment Program of the Company for 2016-2021. The main reasons for adjustment of the Investment Program of IDGC of Centre for 2016-2021 are: actual results of implementation of the Investment Program of the Company in 2015, updating the Company’s obligations on grid connection of customers and taking into account the updated forecast of socio-economic development of the Russian Federation.